## Slide 1: Chapter 7: Project Cost Management
Information Technology Project Management, Ninth Edition
Note: See the text itself for full citations

## Slide 2: Learning Objectives (1 of 2)
Develop a justification for project cost management and its importance in achieving project success
Explain basic project cost management principles, concepts, and terms
Describe the process of planning cost management
Discuss different types of cost estimates and methods for preparing them
Using an example of an information technology (IT) project, list and describe the processes of determining a budget and preparing a cost estimate

## Slide 3: Learning Objectives (2 of 2)
Justify the use of earned value management and project portfolio management to assist in cost control
Describe how project management software can assist in project cost management
Discuss considerations for agile/adaptive environments

## Slide 4: The Importance of Project Cost Management
IT projects have a poor track record for meeting budget goals
  Cost overrun is the additional percentage or dollar amount by which actual costs exceed estimates
  A 2011 Harvard Business Review study reported an average cost overrun of 27 percent
    Most important finding was the discovery of a large number of gigantic overages or “black swans”; a high-impact event that is rare and unpredictable, but not improbable in retrospect

## Slide 5: What Went Wrong?
The United Kingdom’s National Health Service IT modernization program was called the greatest IT disaster in history with an estimated $26 billion overrun
  Program had problems due to incompatible systems, resistance from physicians, and arguments among contractors about who’s responsible for what
  Scrapped in 2011

## Slide 6: What is Cost?
Cost is a resource sacrificed or foregone to achieve a specific objective or something given up in exchange
  Usually measured in monetary units like dollars that must be paid to acquire goods and services

## Slide 7: What is Project Cost Management? (1 of 2)
Project cost management includes the processes required to ensure that the project is completed within an approved budget
  Planning cost management: determining the policies, procedures, and documentation that will be used for planning, executing, and controlling project cost
  Estimating costs: developing an approximation or estimate of the costs of the resources needed to complete a project
  Determining the budget: allocating the overall cost estimate to individual work items to establish a baseline for measuring performance
  Controlling costs: controlling changes to the project budget

## Slide 8: What is Project Cost Management? (2 of 2)

## Slide 9: Basic Principles of Cost Management (1 of 3)
Most members of an executive board better understand and are more interested in financial terms than IT terms; they need to be able to present and discuss project information in both
  Profits: revenues minus expenditures
  Profit margin: ratio of profits to revenues
  Life cycle costing: considers total cost of ownership, or development plus support costs, for a project
  Cash flow analysis: determines estimated annual costs and benefits for a project and resulting annual cash flow

## Slide 10: Media Snapshot
You cannot measure ROI unless you have a benefits measurement process in place
2015 report by PMI findings
  Many organizations do not have a benefits measurement process
  20 percent of organizations report having a high level of benefits realization maturity
  39 percent of high-performing organizations report high benefits realization maturity compared to nine percent of low performers

## Slide 11: What Went Right?
Investing in green IT and other initiatives has helped both the environment and companies’ bottom lines
  Michael Dell, CEO of Dell, reached his goal to make his company “carbon neutral” in 2008
  As of March 2012, Dell had helped its customers save almost $7 billion in energy costs
  In 2014 Dell reported being on track toward reaching their goal of recovering two billion pounds of used electronics by 2020

## Slide 12: Basic Principles of Cost Management (2 of 3)
Types of costs and benefits
  Tangible costs or benefits are those costs or benefits that an organization can easily measure in dollars
  Intangible costs or benefits are costs or benefits that are difficult to measure in monetary terms
  Direct costs are costs that can be directly related to producing the products and services of the project
  Indirect costs are costs that are not directly related to the products or services of the project, but are indirectly related to performing the project
  Sunk cost is money that has been spent in the past; when deciding what projects to invest in or continue, you should not include sunk costs

## Slide 13: Basic Principles of Cost Management (3 of 3)
Additional concepts
  Learning curve theory states that when many items are produced repetitively, the unit cost of those items decreases in a regular pattern as more units are produced
  Reserves are dollars included in a cost estimate to mitigate cost risk by allowing for future situations that are difficult to predict
    Contingency reserves allow for future situations that may be partially planned for (sometimes called known unknowns) and are included in the project cost baseline
    Management reserves allow for future situations that are unpredictable (sometimes called unknown unknowns)

## Slide 14: Advice for Young Professionals
If you have never done so, take a class or do self-study in accounting, financial statements, or financial management
  There are many online resources and short books available on the topics of finance for the non-financial manager, how to use financial statements, or similar content
  Financial specialists are often willing to help less-experienced people better understand the key terminology of the financial field

## Slide 15: Planning Cost Management
The first step in project cost management is planning how the costs will be managed throughout the life of the project
  The project team uses expert judgment, analytical techniques, and meetings to develop the cost management plan
Cost management plan includes:
  Level of accuracy
  Units of measure
  Organizational procedure links
  Control thresholds
  Rules of performance measurement
  Reporting formats
  Process descriptions

## Slide 16: Estimating Costs (1 of 4)
Project managers must take cost estimates seriously if they want to complete projects within budget constraints
  Types of cost estimates
  Tools and techniques for estimating costs
  Typical problems associated with IT cost estimates

## Slide 17: Estimating Costs (2 of 4)
Type of Estimate | When Done | Why Done | Typical Range
Rough order of magnitude (ROM) | Very early in the project life cycle, often 3–5 years before project completion | Provides estimate of cost for selection decisions | -50% to + 100%
Budgetary | Early, 1–2 years out | Puts dollars in the budget plans | -10% to +25%
Definitive | Later in the project, less than 1 year out | Puts dollars in the budget plans | -5% to +10%
Table 7-1 Types of cost estimates

## Slide 18: Estimating Costs (3 of 4)
The number and type of cost estimates vary by application area
  The Association for the Advancement of Cost Engineering International identifies five types of cost estimates for construction projects
    Order of magnitude, conceptual, preliminary, definitive, and control
  Estimates are usually done at various stages of a project
    Should become more accurate as time progresses
  It is important to provide supporting details for estimates and updates to project documents
  A large percentage of total project costs are often labor costs

## Slide 19: Estimating Costs (4 of 4)
Department | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Totals
Information systems | 24 | 31 | 35 | 13 | 13 | 116
Marketing systems | 3 | 3 | 3 | 3 | 3 | 15
Reservations | 12 | 29 | 33 | 9 | 7 | 90
Contractors | 2 | 3 | 1 | 0 | 0 | 6
Totals | 41 | 66 | 72 | 25 | 23 | 227
Table 7-2 Maximum FTE by department by year

## Slide 20: Cost Estimation Tools and Techniques
Analogous or top-down estimates
  Use the actual cost of a previous, similar project as the basis for estimating the cost of the current project
Bottom-up estimates
  Involve estimating individual work items or activities and summing them to get a project total
Three-point estimates
  Involve estimating the most likely, optimistic, and pessimistic costs for items
Parametric estimating
  Uses project characteristics (parameters) in a mathematical model to estimate project costs

## Slide 21: Typical Problems with IT Cost Estimates
Reasons for inaccuracies
  Estimates are done too quickly
  People lack estimating experience
  Human beings are biased toward underestimation
  Management desires accuracy

## Slide 22: How to Develop a Cost Estimate and Basis of Estimates (1 of 3)
See the text for a detailed example of creating a cost estimate for the Surveyor Pro project described in the opening case
  Before creating an estimate gather as much information as possible about the project, ask how the organization plans to use the cost estimate, and clarify the ground rules and assumptions

## Slide 23: How to Develop a Cost Estimate and Basis of Estimates (2 of 3)
Notes: .

## Slide 24: How to Develop a Cost Estimate and Basis of Estimates (3 of 3)

## Slide 25: Best Practice
Alvin Alexander wrote a book called Cost Estimating in an Agile Development Environment in 2015
  Function points are a means of measuring software size in terms that are meaningful to end users
  User stories are a common way to describe requirements in a simple, concise way
  Developers can analyze user stories to estimate the number of internal logical files (ILFs)—a group of logically related data that resides entirely within the application boundary and is maintained through external inputs

## Slide 26: Determining the Budget (1 of 2)
Budgeting involves allocating the project cost estimate to individual work items over time
  Material resources or work items are based on the activities in the WBS for the project
Important goal is to produce a cost baseline
  Time-phased budget that project managers use to measure and monitor cost performance

## Slide 27: Determining the Budget (2 of 2)

## Slide 28: Controlling Costs
Activities involved in controlling project costs
  Monitoring cost performance
  Ensuring that only appropriate project changes are included in a revised cost baseline
  Informing project stakeholders of authorized changes to the project that will affect costs
Several tools and techniques assist in project cost control
  Expert judgment, data analysis, project management information systems, and the to-complete performance index

## Slide 29: Earned Value Management (EVM) (1 of 5)
Project performance measurement technique that integrates scope, time, and cost data
  Given a baseline (original plan plus approved changes), you can determine how well the project is meeting scope, time, and cost goals
Earned value management involves calculating three values for each activity or summary activity from a project’s WBS
  Planned value
  Actual cost
  Earned value

## Slide 30: Earned Value Management (EVM) (2 of 5)
Activity | Week 1
Earned value (EV) | 5,000
Planned value (PV) | 10,000
Actual cost (AC) | 15,000
Cost variance (CV) | -10,000
Schedule variance (SV) | -5,000
Cost performance index (CPI) | 33%
Schedule performance index (SPI) | 50%
Table 7-3 Earned value calculations for one activity after week 1

## Slide 31: Earned Value Management (EVM) (3 of 5)
Term | Formula
Earned value (EV) | EV = PV of all completed work
Cost variance (CV) | CV = EV - AC
Schedule variance (SV) | SV = EV - PV
Cost performance index (CPI) | CPI = EV/AC
Schedule performance index (SPI) | SPI = EV/PV
Estimate at completion (EAC) | EAC = BAC/CPI
Estimated to Complete (ETC) | ETC = EAC - AC
Table 7-4 Earned value formulas

## Slide 32: Earned Value Management (EVM) (4 of 5)
Important concepts
  Cost variance (CV) is the earned value minus the actual cost
  Schedule variance (SV) is the earned value minus the planned value
  Cost performance index (CPI) is the ratio of earned value to actual cost
  Schedule performance index (SPI) is the ratio of earned value to planned value
  Estimate at completion (EAC) is an estimated cost of completing a project based on performance to date
  To-complete performance index (TCPI) is a measure of the cost performance that must be achieved with the remaining resources to meet a specific goal

## Slide 33: Earned Value Management (EVM) (5 of 5)

## Slide 34: Global Issues (1 of 2)
EVM is used worldwide, and it is particularly popular in the Middle East, South Asia, Canada, and Europe
  Most countries require EVM for large defense or government projects, as shown in Figure 7-7
  EVM is also used in such private-industry sectors as IT, construction, energy, and manufacturing.
    However, most private companies have not yet applied EVM to their projects because management does not require it, feeling it is too complex and not cost effective

## Slide 35: Global Issues (2 of 2)

## Slide 36: Project Portfolio Management
Many organizations collect and control an entire suite of projects or investments as one set of interrelated activities in a portfolio
Five levels for project portfolio management
  Put all your projects in one database
  Prioritize the projects in your database
  Divide your projects into two or three budgets based on type of investment
  Automate the repository
  Apply modern portfolio theory, including risk-return tools that map project risk on a curve

## Slide 37: Using Project Management Software to Assist in Project Cost Management (1 of 2)
Spreadsheets are a common tool for resource planning, cost estimating, cost budgeting, and cost control
  Many companies use more sophisticated and centralized financial applications software for cost information
Project management software can increase a project manager’s effectiveness during each process of project cost management
  Many IT project managers use other tools to manage cost information because they do not know that they can use project management software, or they do not track costs based on a WBS, as most project management software does

## Slide 38: Using Project Management Software to Assist in Project Cost Management (2 of 2)
Recent Studies on PPM Software
  2017 Gartner report says the market continues to grow, with annual sales over $2.3 billion
  Forrester estimates ROIs of 250 percent from PPM tools
  Pfizer and Ford use PPM software to improve transparency of the many projects they manage

## Slide 39: Considerations for Agile/Adaptive Environments
AgileEVM is an adapted implementation of EVM
  Uses the Scrum framework artifacts as inputs, uses traditional EVM calculations, and is expressed in traditional EVM metrics
  Requires a minimal set of input parameters
    Actual cost of a project, an estimated product backlog, a release plan that provides information on the number of iterations in the release and the assumed velocity
  All estimates can be in hours, story-points, team days or any other consistent estimate of size
    The critical factor is that it must be a numerical estimate of some kind

## Slide 40: Chapter Summary
Project cost management is a traditionally weak area of IT projects
  Project managers must understand several basic principles of cost management to be effective in managing project costs
Main processes
  Plan cost management
  Estimate costs
  Determine the budget
  Control costs
Several software products can assist with project cost management