## Slide 1
Project progress control (PPC) (software project tracking)
Ily Amalina Ahmad Sabri
Aziz Deraman
Topic 5: Software Management

## Slide 2: Project delay
Mainly failures of management – cause by situations:
  Overly / blindly optimistics scheduling and budgeting
  Unprofesional softwatre risk management
  Belated identification of schedule and budget diffifculties and/or under-estimate of their extent

## Slide 3: Components of PPC
Control of risk management activities
Project schedule control
Project resource control
Project budget control

## Slide 4: Components of PPC
Control of risk management activities
  Refer to items listed in the contract review/ project plan
  The team has to apply systematic risk management activities
  Periodical assessment about the state of software risk
  Project manager should intervene to provide help in high risk cases

## Slide 5: Components of PPC
Project schedule control
  Deals with project’s compliance witrhb its approved and contracted timetables.
  Follow-up is based on milestone
  Management will focus its control activities on critical delays, it those will substantially affect final completion of the project
  Intervention: providing additional resources and reschedulling

## Slide 6: Components of PPC
Project resource control
  Mainly focus on professional human resources
  Other assets: soft dev and testing faicilities
  Any deviation in resource utilization may affect performance of other project within the org
  Main problem: most of identified deviation cases were identified at much later stage of the project … require management intervention

## Slide 7: Components of PPC
Project budget control
  Based on the comparison of actual with scheduled expenditures
  The main budget items demanding control are:
    Human resources
    Dev and testing facilities
    Purchase of COTS software
    Purchase of hardware
    Payments to subcontractors
  Budget control based on milestones and periodic reports – facilitate early identification of budget overruns.
  This is the highest priority to management – tend to neglect other components!!!!

## Slide 8: Progress Control of internal project
Project undertaken by other departments such as supporting marketing packages etc
Tend to occupy a lower place among management’s priorities
  Less attention  inappropriate follow-up
  Results: budget overruns

## Slide 9: Progress Control of external participants
To include subcontractors, suppliers of COTS software and reused sofware modules,… the customer himself
PPC mainly focus on project’s schedules and the risks identified in planned project activities

## Slide 10: Implementing PPC regimes
Mainly based on procedures that determine:
  The allocation of responsibility for the process control task:
    Size of management unit
    Frequency of reporting
    Situations requiring immediate reporting to upper management
  Management audits of project progress
    How well progress reports are transmitted
    The specific mamagement control activities to be initiated

## Slide 11: Implementing PPC regimes
Software tools with wellknown approaches such PERT/CPM etc